## Sheet1
Task | Start Date | End Date | Days Left | Assigned | Date Today: | 2018-08-06
Finalization (Chapter 1-3) | 2018-08-26 | 2018-08-29 | 23
Topic Identification | 2018-08-05 | 2018-08-10 | 4
Research | 2018-08-05 | 2018-08-17 | 11
Writing of Chapter 1 |  | 2018-08-23 | 17
Writing of Background of the Study |  |  | 0
Writing of Statement of the Problem |  |  | 0
Writing of Hypothesis |  |  | 0
Writing of Theoretical Framework |  |  | 0
Writing of Conceptual Framework |  |  | 0
Writing of Significance of Study |  |  | 0
Writing of Scope and Limitation |  |  | 0
Writing of Operational Terms |  |  | 0
Writing of Chapter 2 |  | 2018-08-25 | 19 | Marzo, Pauline
Writing of Related Literature |  | 2018-08-25 | 19 | Marzo, Pauline
Writing of Related Studies |  | 2018-08-25 | 19 | Marzo, Pauline
Writing of Synthesis of the Study |  | 2018-08-25 | 19 | Marzo, Pauline
Writing of Chapter 3 |  |  | 0
Writing of Research Design |  |  | 0
Writing of Source of Data |  |  | 0
Writing of Sampling Techniques |  |  | 0
Writing of Instrumentation |  |  | 0
Writing of System Architecture |  |  | 0
Writing of Development Details |  |  | 0
Writing of Research Instrument |  |  | 0
Writing of Data Generration/Gathering Procedure |  |  | 0
Writing of Statistical Treatment of Data |  |  | 0
0
0
0
0
0
0
0
0