## Sheet1
Task | Start Date | End Date | Days Left | Status | Assigned | Date Today: | 2018-08-07
Finalization (Chapter 1-3) Proofreading Done | 2018-08-26 | 2018-08-29 | 22
Topic Identification | 2018-08-05 | 2018-08-10 | 3 | Doing | Group
Research | 2018-08-05 | 2018-08-17 | 10 |  | Group
Writing of Chapter 1 | 2018-08-07 | 2018-08-23 | 16 |  | Group
Writing of Background of the Study | 2018-08-07 | 2018-08-08 | 1 |  | Mercado, Nel
Writing of Statement of the Problem | 2018-08-07 | 2018-08-08 | 1 |  | Marzo, Pauline
Writing of Hypothesis |  | 2018-08-23 | 16 |  | Group
Writing of Theoretical Framework |  | 2018-08-23 | 16 |  | Group
Writing of Conceptual Framework |  | 2018-08-23 | 16 |  | Alcala, Michael
Writing of Significance of Study |  | 2018-08-23 | 16 |  | Mercado, Nel
Writing of Scope and Limitation |  | 2018-08-23 | 16 |  | Garcia, Jasper
Writing of Operational Terms |  | 2018-08-23 | 16 |  | Marzo, Pauline
Writing of Chapter 2 |  | 2018-08-25 | 18 |  | Marzo, Pauline
Writing of Related Literature |  | 2018-08-25 | 18 |  | Marzo, Pauline
Writing of Related Studies |  | 2018-08-25 | 18 |  | Marzo, Pauline
Writing of Synthesis of the Study |  | 2018-08-25 | 18 |  | Marzo, Pauline
Writing of Chapter 3 |  | 2018-08-27 | 20
Writing of Research Design |  | 2018-08-27 | 20
Writing of Source of Data |  | 2018-08-27 | 20
Writing of Sampling Techniques |  | 2018-08-27 | 20
Writing of Instrumentation |  | 2018-08-27 | 20
Writing of System Architecture |  | 2018-08-27 | 20
Writing of Development Details |  | 2018-08-27 | 20
Writing of Research Instrument |  | 2018-08-27 | 20
Writing of Data Generation/Gathering Procedure |  | 2018-08-27 | 20
Writing of Statistical Treatment of Data |  | 2018-08-27 | 20
0
0
0
0
0
0
0
0